## Sheet1
Folding Table Remaining Work and Possible Upgrades
General
Ensure all endstops are installed and connected.
They are driven Normally Open (NO). When the endstop is activated a circuit is formed and broken when not. Use a pin with INPUT_PULLUP enabled on it connected to one end of the switch with the other end of the switch connected to ground. An activation has occured if the read voltage on the pin drops to near zero. The mirrored endstops on left and right sides should be joined to the same pin.
Side Carraiges
Use dremel/rotary tool to cut notches into the lock pins protruding outside the carriage.
These will hold the handle in place.
Handle should be printed from a thermoplastic and designed for an interference fit
To install use a heat gun on low to heat the base of the handle until slightly malleable, press it onto the pin end, then use a rag to squeeze around the base ensuring the material is locked in by the notches.
Print and install bearing pad shims
Sizes 0.5mm, 1mm, 1.5mm, 2mm are in the designs. The peel apart 8020 ones may be used to finely adjust.
Pnumatics
Build pressure regulator system (with teflon on threads to prevent leaks)
Adjustable pressure range, air filter, master on-off valve, quick-connect
(optional) Replace valves with pnumatic solenoids
If going with solenoids to control the clamps from the controller screen:Use a 12V pnumatic solenoid threaded for 1/4NTP push-connect fittings. A relay driven by an octocoupler connected to an arduino pin must be used to switch the 12V source to the solenoid due to the voltage level and current draw.
Programming
Create an auto-homing method making use of the endstops to move to extents, thus mapping the capable size and zeroing the initial position
Will need to keep in mind motor direction, any endstop inverting, and default position offsets (as measured from the center of the housing)
Bug in the input screen allowing for multiple demical points in the number, breaking the float variables when done.
Calibration
Use the CMM Arm to get calibrated initial offsets when using for the first time. (Measured from cylinder shaft center)
The distance from the housing center to the extents of the clamp center at their min and max positions are key. These values will offset the default values from 0 to the actual position fo the clamp.
Unfix the leadscrew couplers and turn each side by hand until the top/bottom carraiges are centered and flush
Possible Upgrades
Use a phototransistor/photoresistor to determine if a cushion is put in the clamp location to automatically engage it some period after detection OR use the same as a non-contact switch (possibly on top the clamp plate) to trigger it manually.